## Schedule
Lane | Task | Status | Start | End | Duration Days | Notes
Corporate Shadows | Revised videos 1-3 private upload complete | Done | 2026-05-28 | 2026-05-28 | 1 | Revised replacements uploaded as private drafts
Corporate Shadows | Audit current video queue and visual quality | Active | 2026-05-29 | 2026-05-31 | 3 | Identify visual blockers before public publishing
Corporate Shadows | Upgrade visual sourcing/generation workflow | Planned | 2026-06-01 | 2026-06-07 | 7 | Move beyond placeholder visuals
Corporate Shadows | Rebuild video 4 visuals and QC | Planned | 2026-06-08 | 2026-06-11 | 4 | Sugar lobby episode
Corporate Shadows | Rebuild video 5 visuals and QC | Planned | 2026-06-12 | 2026-06-15 | 4 | East India Company episode
Corporate Shadows | Prepare videos 6-8 scripts and research | Planned | 2026-06-16 | 2026-06-25 | 10 | Next Corporate Shadows queue
Corporate Shadows | Produce videos 6-8 | Planned | 2026-06-26 | 2026-07-09 | 14 | Generate voiceover, visuals, edit, QC
Corporate Shadows | Corporate analytics and packaging iteration | Planned | 2026-07-10 | 2026-07-23 | 14 | Improve CTR/retention based on data
Corporate Shadows | Corporate sponsorship/newsletter planning | Planned | 2026-07-24 | 2026-08-06 | 14 | Set up non-AdSense monetization path
Saints in the Shadows | Source library and channel config complete | Done | 2026-05-28 | 2026-05-28 | 1 | Saints source base and config created
Saints in the Shadows | Saint Seraphim research and outline complete | Done | 2026-05-28 | 2026-05-28 | 1 | Research brief and outline completed
Saints in the Shadows | Saint Seraphim full script package | Active | 2026-05-29 | 2026-06-02 | 5 | Full long-form script, no upper cap
Saints in the Shadows | Saints branding and channel setup plan | Planned | 2026-06-03 | 2026-06-07 | 5 | Name, banner, avatar, channel description
Saints in the Shadows | Saint Seraphim scene table and visuals | Planned | 2026-06-08 | 2026-06-13 | 6 | Scene plan and visual prompts
Saints in the Shadows | Saint Seraphim voiceover/edit/QC | Planned | 2026-06-14 | 2026-06-20 | 7 | Create first private draft
Saints in the Shadows | Create actual Saints YouTube channel | Milestone | 2026-06-17 | 2026-06-17 | 1 | Separate YouTube channel/Brand Account
Saints in the Shadows | Upload Saint Seraphim as private draft | Milestone | 2026-06-21 | 2026-06-21 | 1 | Private draft first
Saints in the Shadows | Saint Paisios research/script package | Planned | 2026-06-22 | 2026-07-01 | 10 | Second saints episode package
Saints in the Shadows | Saint Silouan research/script package | Planned | 2026-07-02 | 2026-07-11 | 10 | Third saints episode package
Saints in the Shadows | Produce Saints episodes 2-3 | Planned | 2026-07-12 | 2026-07-29 | 18 | Build draft queue
Saints in the Shadows | Saints launch packaging and first public publish | Planned | 2026-07-30 | 2026-08-05 | 7 | Launch window
AI/B2B Automation | Define channel concept and offer map | Planned | 2026-06-10 | 2026-06-14 | 5 | Audience, offers, monetization
AI/B2B Automation | Research 30 workflow topics | Planned | 2026-06-15 | 2026-06-21 | 7 | Based on official docs and market needs
AI/B2B Automation | Build/test first 5 real automations | Planned | 2026-06-22 | 2026-07-05 | 14 | No generic AI news
AI/B2B Automation | Create templates/downloadables | Planned | 2026-07-06 | 2026-07-15 | 10 | Monetization assets
AI/B2B Automation | Record 3 pilot tutorials | Planned | 2026-07-16 | 2026-07-25 | 10 | Private pilots
AI/B2B Automation | Create AI/B2B channel branding | Planned | 2026-07-26 | 2026-07-30 | 5 | Branding package
AI/B2B Automation | Upload 3 private pilot videos | Planned | 2026-07-31 | 2026-08-04 | 5 | Private review first
AI/B2B Automation | Launch AI/B2B channel if pilots are strong | Milestone | 2026-08-07 | 2026-08-07 | 1 | Launch decision
AI/B2B Automation | Publish weekly AI/B2B tutorials | Planned | 2026-08-07 | 2026-08-20 | 14 | Weekly cadence
Shared Systems | Agent prompt library complete | Done | 2026-05-28 | 2026-05-28 | 1 | Reusable production agents created
Shared Systems | Build shared content calendar | Planned | 2026-06-01 | 2026-06-04 | 4 | Cross-channel planning
Shared Systems | Separate upload queues per channel | Planned | 2026-06-05 | 2026-06-09 | 5 | Prevent wrong-channel uploads
Shared Systems | Analytics dashboard design | Planned | 2026-06-10 | 2026-06-16 | 7 | Portfolio metrics
Shared Systems | Sponsorship/affiliate tracking system | Planned | 2026-07-15 | 2026-07-24 | 10 | Business monetization tracking

## Weekly Gantt
Lane | Task | Status | Start | End | May 28 | Jun 04 | Jun 11 | Jun 18 | Jun 25 | Jul 02 | Jul 09 | Jul 16 | Jul 23 | Jul 30 | Aug 06 | Aug 13 | Aug 20
Corporate Shadows | Revised videos 1-3 private upload complete | Done | 2026-05-28 | 2026-05-28
Corporate Shadows | Audit current video queue and visual quality | Active | 2026-05-29 | 2026-05-31
Corporate Shadows | Upgrade visual sourcing/generation workflow | Planned | 2026-06-01 | 2026-06-07
Corporate Shadows | Rebuild video 4 visuals and QC | Planned | 2026-06-08 | 2026-06-11
Corporate Shadows | Rebuild video 5 visuals and QC | Planned | 2026-06-12 | 2026-06-15
Corporate Shadows | Prepare videos 6-8 scripts and research | Planned | 2026-06-16 | 2026-06-25
Corporate Shadows | Produce videos 6-8 | Planned | 2026-06-26 | 2026-07-09
Corporate Shadows | Corporate analytics and packaging iteration | Planned | 2026-07-10 | 2026-07-23
Corporate Shadows | Corporate sponsorship/newsletter planning | Planned | 2026-07-24 | 2026-08-06
Saints in the Shadows | Source library and channel config complete | Done | 2026-05-28 | 2026-05-28
Saints in the Shadows | Saint Seraphim research and outline complete | Done | 2026-05-28 | 2026-05-28
Saints in the Shadows | Saint Seraphim full script package | Active | 2026-05-29 | 2026-06-02
Saints in the Shadows | Saints branding and channel setup plan | Planned | 2026-06-03 | 2026-06-07
Saints in the Shadows | Saint Seraphim scene table and visuals | Planned | 2026-06-08 | 2026-06-13
Saints in the Shadows | Saint Seraphim voiceover/edit/QC | Planned | 2026-06-14 | 2026-06-20
Saints in the Shadows | Create actual Saints YouTube channel | Milestone | 2026-06-17 | 2026-06-17 |  |  | ?
Saints in the Shadows | Upload Saint Seraphim as private draft | Milestone | 2026-06-21 | 2026-06-21 |  |  |  | ?
Saints in the Shadows | Saint Paisios research/script package | Planned | 2026-06-22 | 2026-07-01
Saints in the Shadows | Saint Silouan research/script package | Planned | 2026-07-02 | 2026-07-11
Saints in the Shadows | Produce Saints episodes 2-3 | Planned | 2026-07-12 | 2026-07-29
Saints in the Shadows | Saints launch packaging and first public publish | Planned | 2026-07-30 | 2026-08-05
AI/B2B Automation | Define channel concept and offer map | Planned | 2026-06-10 | 2026-06-14
AI/B2B Automation | Research 30 workflow topics | Planned | 2026-06-15 | 2026-06-21
AI/B2B Automation | Build/test first 5 real automations | Planned | 2026-06-22 | 2026-07-05
AI/B2B Automation | Create templates/downloadables | Planned | 2026-07-06 | 2026-07-15
AI/B2B Automation | Record 3 pilot tutorials | Planned | 2026-07-16 | 2026-07-25
AI/B2B Automation | Create AI/B2B channel branding | Planned | 2026-07-26 | 2026-07-30
AI/B2B Automation | Upload 3 private pilot videos | Planned | 2026-07-31 | 2026-08-04
AI/B2B Automation | Launch AI/B2B channel if pilots are strong | Milestone | 2026-08-07 | 2026-08-07 | [10 empty] | ?
AI/B2B Automation | Publish weekly AI/B2B tutorials | Planned | 2026-08-07 | 2026-08-20
Shared Systems | Agent prompt library complete | Done | 2026-05-28 | 2026-05-28
Shared Systems | Build shared content calendar | Planned | 2026-06-01 | 2026-06-04
Shared Systems | Separate upload queues per channel | Planned | 2026-06-05 | 2026-06-09
Shared Systems | Analytics dashboard design | Planned | 2026-06-10 | 2026-06-16
Shared Systems | Sponsorship/affiliate tracking system | Planned | 2026-07-15 | 2026-07-24

## Milestones
Date | Milestone | Lane | Decision / Output
2026-06-17 | Create actual Saints YouTube channel | Saints in the Shadows | Separate Brand Account / channel target exists
2026-06-21 | Upload Saint Seraphim private draft | Saints in the Shadows | First saints draft ready for review
2026-07-15 | Corporate visual workflow checkpoint | Corporate Shadows | Decide if videos 6-8 can be produced reliably
2026-08-05 | AI/B2B pilot review | AI/B2B Automation | Launch only if tutorials are useful and template-backed
2026-08-20 | Portfolio review | Shared Systems | Allocate capacity based on results